## Instructions
ACA BEAD - Attachment 5 : Project Timeline Template Instructions
Applicant Name
Project Area ID
Below are instructions to complete the template:
Applicants are required to provide details of the proposed project schedule with the following instructions:
Applicants should use the Blue color to fill the Gantt chart based on the start and finish dates of each phase/milestone.
General Instructions | For each phase/milestone, provide the following: -Start Date -Duration -Date for 25% Project Completion -Date for 50% Project Completion -Date for 75% Project Completion -End Date (100% Completion)
The project start (the beginning of Month 1) occurs when a subgrantee receives the subgrant from ACA. The start of each individual milestone must be provided in relation to the project start. Applicants are welcome to provide their assumption of the project start date. All other referenced dates within the schedule will be contingent on the project start date.
Applicants may add more rows in this workbook to include more Key Implementation Phases/Milestones.
The milestones must only encompass BEAD-funded deployment activities. Items such as ongoing maintenance should not be included in the timeline.
Applicants are required to deploy the planned broadband network and begin providing services to each customer that desires broadband service within the project area not later than four years after the date on which the subgrantee receives the subgrant from ACA, and project milestones may not extend beyond the four-year timeframe (48 months).

## Project Timeline
Key Implementation Phase / Milestone | Brief Description of Phase / Milestone | Start Date | Duration (Months) | Date for 25% Completion | Date for 50% Completion | Date for 75% Completion | End Date (100% Completion) | Month #1 | Month #2 | Month #3 | Month #4 | Month #5 | Month #6 | Month #7 | Month #8 | Month #9 | Month #10 | Month #11 | Month #12 | Month #13 | Month #14 | Month #15 | Month #16 | Month #17 | Month #18 | Month #19 | Month #20 | Month #21 | Month #22 | Month #23 | Month #24 | Month #25 | Month #26 | Month #27 | Month #28 | Month #29 | Month #30 | Month #31 | Month #32 | Month #33 | Month #34 | Month #35 | Month #36 | Month #37 | Month #38 | Month #39 | Month #40 | Month #41 | Month #42 | Month #43 | Month #44 | Month #45 | Month #46 | Month #47 | Month #48
Phase 1 | [Description] | [Date] | [Number] | [Date] | [Date] | [Date] | [Date] | bar: Month #1 to Month #8
Milestone 1 | bar: Month #3 to Month #8
Milestone 2
Milestone 3
Phase 2
Milestone 4
Milestone 5
Milestone 6